## Full Audit
PULSE BY CONEXUS — COMPLETE SYSTEM AUDIT REPORT ¦ v3.1 Specification vs Current Implementation
Module Name | Feature Name | Requirement (from PDF) | Implementation Status | Completion % | Gap / Issue Description | Recommended Fix (Step-by-step) | Priority | Impact | Notes
System Architecture | Laravel 11 + PHP 8.3 | Backend on Laravel 11 with PHP 8.3, MVC, Eloquent ORM, queues, scheduling, policies | Completed | 100% | None. Stack fully aligned with spec. | No action required. | Low | Technical | Confirmed in implementation notes.
System Architecture | MySQL 8 Database | Relational integrity for all HR data; indexing strategy per Section 6.1 | Completed | 100% | Core DB implemented. Index strategy not explicitly verified. | Verify composite indexes on attendance_logs (employee_id, date), leave_balances (employee_id, leave_type_id, financial_year), notifications (notifiable_id, read_at). Run EXPLAIN on frequent queries. | Medium | Technical / Performance | Index gaps may slow reporting at scale.
System Architecture | Livewire 3 + Blade + Tailwind | Reactive UI server-rendered; fully responsive; no separate JS framework | Completed | 100% | None. | No action required. | Low | Technical
System Architecture | In-App Notifications (Database Channel) | Bell icon with unread badge, Livewire polling every 30 sec, Mark-all-read | Completed | 100% | None. Livewire polling confirmed. | No action required. | Low | UX
System Architecture | Email via SMTP (Payslip Delivery) | SMTP email ONLY for: payslip PDF attached, account created/reset, final settlement | Partial | 40% | SMTP configured for basic alerts only. Payslip PDF email not implemented because PDF generation itself is not using dompdf yet. | 1. Install barryvdh/laravel-dompdf via composer. 2. Create PayslipPdf blade view. 3. In PayrollService@issuePayslip(): generate PDF → store via Storage → send via Mail::to($employee->email)->send(new PayslipMailed($payslip)). 4. Set emailed_at on payslip record. 5. Configure SMTP creds in .env. | Critical | HR / Finance / Compliance | Employees cannot receive payslips until fixed. Go-live blocker.
System Architecture | Payslip PDF (barryvdh/laravel-dompdf) | PDF generation via dompdf package for payslip + letters | Deviated | 20% | Currently using browser @media print CSS. dompdf not installed. Cannot email PDFs or serve signed URLs. | 1. composer require barryvdh/laravel-dompdf. 2. Create resources/views/payslips/pdf.blade.php with all payslip fields. 3. In PayrollService: $pdf = PDF::loadView('payslips.pdf', $data)->save(storage_path(...)). 4. Store pdf_path on payslip record. 5. Serve via signed route: URL::temporarySignedRoute('payslip.download', now()->addMinutes(5), ['id'=>$id]). | Critical | Finance / HR / Compliance | Go-live blocker. Email delivery depends on this.
System Architecture | Signed URLs for Payslip Download | Temporary signed URLs expiring in 5 minutes for payslip PDF downloads | Partial | 0% | Not implemented. Currently browser print only. | In PayslipController@download(): validate request->hasValidSignature(); return Storage::response($payslip->pdf_path). Route definition: Route::get('/payslips/{id}/download', [PayslipController::class,'download'])->name('payslip.download')->middleware('signed'). | High | Security / Compliance | Security requirement per Section 9.
System Architecture | DB Backups (spatie/laravel-backup) | Daily MySQL dump, retain 30 days | Missing | 0% | Not implemented. | 1. composer require spatie/laravel-backup. 2. Publish config: php artisan vendor:publish --provider=Spatie\Backup\BackupServiceProvider. 3. Set backup.destination.disks and backup.cleanup.defaultStrategy.keepDailyBackupsForDays=30 in config/backup.php. 4. Add to scheduler: $schedule->command('backup:run')->daily()->at('02:00'). 5. Add $schedule->command('backup:clean')->daily(). | Critical | Compliance / Operations | Data loss risk. Go-live blocker.
RBAC | Role Enum on Users Table | 6 roles: super_admin, hr_admin, director, manager, finance, employee | Completed | 100% | None. | No action required. | Low | Security
RBAC | Laravel Policies & Gates | EmployeePolicy, LeavePolicy, AttendancePolicy, PayrollPolicy enforced at controller + Blade layer | Completed | 100% | 4 policies confirmed. | Also create OTPolicy and IncentivePolicy per spec RBAC table (Section 4). | Medium | Security | Missing OT and Incentive policies.
RBAC | System Config Settings Access | Super Admin = Full; HR Admin = Partial for system settings (shift config, cycle assignment, MDL setup) | Partial | 30% | UI mapping for system config not built. HR Admin partial access not demarcated. | 1. Create SystemSettingsController with middleware('role:super_admin,hr_admin'). 2. In Blade: @can('manageFullSettings') show shift/MDL create forms @else show read-only config @endcan. 3. Gate::define('manageFullSettings', fn($u)=>$u->role==='super_admin'). 4. Partial access for HR Admin: allow shift_settings edits, block department/role management. | High | HR / Operations
RBAC | Finance Role — Compensation + Read-Only Attendance | Finance sees full Compensation module + read-only employee/attendance summary | Completed | 100% | Confirmed via PayrollPolicy. | No action required. | Low | Finance
RBAC | Shivani HR Admin Secondary Permissions Flag | HR Admin has Manager-level read access across ALL departments via secondary permissions flag | Partial | 50% | Role exists but cross-department read flag not explicitly implemented as a secondary permission. | Add a boolean column hr_cross_department_read (default false) on users table. Set true for Shivani's account. In queries scoped to department, add: if(auth()->user()->hr_cross_department_read) remove department_id filter. | Medium | HR
Employee Management | Employee CRUD + Directory | Full profile: name, email, phone, emergency contact, DOB, gender, address, photo; CRUD; org chart | Completed | 100% | None. | No action required. | Low | HR
Employee Management | salary_cycle Field (A/B) | salary_cycle (A/B) on employment_details drives which payroll_run employee belongs to each month | Partial | 60% | Field may not be confirmed in employment_details. Payroll separation by cycle not verified. | 1. Confirm salary_cycle ENUM('A','B') exists on employment_details. 2. In PayrollService@generateRun($cycle, $month, $year): Employee::whereHas('employmentDetail', fn($q)=>$q->where('salary_cycle',$cycle))->get(). 3. Ensure HR Admin UI allows cycle change with effective_from date. 4. Add migration if column missing: $table->enum('salary_cycle',['A','B'])->default('A'); | Critical | Finance / Payroll | Without this, Cycle A and B payroll runs are impossible. Go-live blocker.
Employee Management | Employee Lifecycle States | States: active, probation, notice_period, inactive (archived, never deleted) | Completed | 100% | Confirmed. | No action required. | Low | HR
Employee Management | Org Chart (manager_id hierarchy) | Hierarchy view rendered from manager_id relationships | Completed | 100% | Confirmed. | No action required. | Low | HR / Operations
Attendance | Clock In/Out with Work Mode | Web dashboard button; work_mode (Office/WFH) selected at clock-in; IP address logged as soft audit | Completed | 100% | None. | No action required. | Low | HR / Operations
Attendance | Break Logging (Repeatable) | Start/End Break repeatable; each segment recorded; total break informational; hours NOT deducted | Completed | 100% | Confirmed. | No action required. | Low | HR
Attendance | Excess Break Flag (>60 mins) | Flag raised if total break > 60 mins; in-app notification to employee + manager | Partial | 60% | Manual logic exists; automated cron pulse:check-excess-breaks not implemented. | Create app/Console/Commands/CheckExcessBreaks.php: query break_logs grouped by attendance_log_id for today, SUM(duration_minutes)>60 → set excess_break_flag=true on attendance_logs → dispatch ExcessBreakNotification to employee and manager. | High | HR / Operations | Depends on cron job being built.
Attendance | Missing Clock-Out Flag | Flag if no clock-out by shift_end + 1 hour; in-app notification to employee | Completed | 100% | pulse:check-missing-checkouts implemented at Daily 21:00. | No action required. | Low | HR
Attendance | Late Flag per Shift | IT Shift: >10:35 AM = Late. UK Sales: >1:05 PM = Late. Based on configurable shift_settings grace_minutes=5 | Partial | 50% | Core logic exists but shift_settings table (configurable grace) may not be built. Cron pulse:check-late-arrivals pending. | 1. Ensure shift_settings table exists with: shift_name, start_time, end_time, standard_hours, grace_minutes(5), max_break_minutes(60), ot_threshold_hours(9). 2. Seed IT and UK shifts. 3. Create CheckLateArrivals command: at 10:45 check IT shift employees; at 13:15 check UK shift. Compare clock_in vs shift start+grace. Set late_flag=true. Notify manager. 4. Schedule: $schedule->command('pulse:check-late-arrivals')->dailyAt('10:45') and ->dailyAt('13:15'). | Critical | HR / Operations | Go-live blocker. Late tracking is core HR function.
Attendance | Attendance Regularisation Workflow | Employee submits date + correct times + reason → manager approves/rejects → original values in audit trail → employee notified | Completed | 100% | Confirmed. | Verify that on approval, original clock_in/clock_out values are stored in audit trail (audit_logs or regularisation notes field) before overwriting attendance_log. | Medium | HR / Compliance
Attendance | OT Hours Calculation | OT hours = total_hours − 9 ONLY if approved ot_request exists for that date | Completed | 100% | Confirmed in OTService. | No action required. | Low | Finance
Attendance | shift_settings Table (Configurable) | Configurable shift table driving grace period, max break, OT threshold per shift | Partial | 40% | Table may not be fully built or seeded. Used as hard-coded values instead. | 1. Migration: create shift_settings with all columns per spec. 2. Seed: IT Shift (10:30,19:30,9hrs,5min grace,60min break,9hr OT threshold) and UK Shift (13:00,22:00,9hrs,5min,60min,9hr). 3. employment_details.shift FK → shift_settings.id. 4. All AttendanceService logic reads from shift_settings dynamically. | High | HR / Operations | Hard-coding shifts = risk when policy changes.
Leave Management | CSL (12 days) + No Lapse Policy | 12 CSL days per July–June year; unused balance carries forward indefinitely, no auto-reset | Completed | 100% | Confirmed. | No action required. | Low | HR
Leave Management | MDL (6 days) — Mandatory December Leave | 6 pre-blocked December days; employees cannot apply other leave on MDL days; working MDL earns Comp Off | Partial | 20% | MDL logic not implemented. december_mandatory_days table and Comp Off auto-credit missing. | 1. Create december_mandatory_days migration: id, date, year, is_comp_off_eligible. 2. Seed 6 days per December year. 3. In LeaveService@validateRequest(): check if any requested date falls in december_mandatory_days → reject with message. 4. Add attendance cron: daily check if employee clocked in on a MDL day → credit 1 Comp Off via leave_balances (comp_off_credits += 1). 5. Ensure MDL days are pre-blocked in leave calendar UI. | Critical | HR / Compliance | Go-live blocker. Leave calculation will be wrong without MDL blocking.
Leave Management | Comp Off — Earn + Carry Forward | Earn 1 CO when working on MDL day or UK public holiday; CO carries forward indefinitely | Missing | 0% | No Comp Off crediting logic exists. | 1. Confirm comp_off_credits column on leave_balances. 2. In AttendanceService@clockOut(): if date in december_mandatory_days OR public_holidays AND employee worked → increment comp_off_credits. 3. Add CO balance to Employee Dashboard leave widget. 4. Allow CO to be applied like CSL in leave request flow (leave_type_id = CO type). | High | HR / Compliance
Leave Management | Public Holidays (UK Calendar) | Non-working days; no leave consumed; working on them earns Comp Off | Missing | 0% | public_holidays table not populated/referenced in leave logic. | 1. Seed public_holidays for current year (UK bank holidays + India national holidays as applicable). 2. In LeaveService@validateRequest(): if date in public_holidays → inform employee it is a public holiday, no leave deducted. 3. Wire into Comp Off earning logic (see above). | High | HR / Compliance
Leave Management | Leave Encashment Workflow | Employee requests encashment of CSL days → Director + HR Admin approve → amount fed into payroll_month as line item | Partial | 20% | leave_encashment_requests table may not be wired to payroll; approval workflow not confirmed. | 1. Create leave_encashment_requests migration per spec schema. 2. LeaveEncashmentController@store(): validate CSL balance ≥ days_requested. Set status=pending. Notify Director + HR Admin. 3. On approval: deduct from leave_balances.used_days; calculate encashment_amount (days × daily_rate from salary_structure); set payroll_month_id to current payroll_run. 4. In PayrollService@calculate(): include approved encashment_amount in net_pay calculation. 5. Notify employee in-app. | Critical | Finance / HR | Go-live blocker. Payroll calculation will be incomplete.
Leave Management | Leave Approval + 24-hr Escalation | Manager approves/rejects; if no action in 24 hrs → escalation notification to HR Admin | Completed | 100% | Confirmed (hourly cron + escalation implemented). | No action required. | Low | HR
Leave Management | Half-Day Leave | CSL supports half-day flag; MDL and Comp Off do not | Partial | 70% | Half-day flag exists on leave_requests. MDL restriction not enforced. | In LeaveService: if leave_type=MDL → force half_day=false. If leave_type=CO → force half_day=false. | Medium | HR
Overtime | OT Pre-Approval Workflow | Employee submits OT request before working late; manager approves; in-app notifications both ways | Completed | 100% | Confirmed. | No action required. | Low | Finance / HR
Overtime | OT Rate ₹100/hr Fixed | Flat ₹100/hr, no differential. OT hours = total_hours − 9 if approved request exists | Completed | 100% | Confirmed. ot_rate stored as 100 on overtime_records. | No action required. | Low | Finance
Overtime | OT Escalation Cron (24-hr) | Hourly cron: find OT requests pending > 24 hrs; notify HR Admin | Missing | 0% | pulse:check-ot-escalations not implemented. | Create CheckOtEscalations command (mirror of CheckLeaveEscalations). Query ot_requests WHERE status=pending AND created_at < NOW()-24hrs AND escalated_at IS NULL. Dispatch HrAdminOtEscalationNotification. Set escalated_at. Schedule: ->everyHour(). | High | HR / Operations
Overtime | Monthly OT Summary for Finance | OT hours + amount auto-populated in monthly summary; Finance verifies before payslip generation | Completed | 100% | Confirmed in overtime_records. | No action required. | Low | Finance
Compensation & Finance | Salary Cycle A/B Separation | Separate payroll_runs for Cycle A (1–31) and Cycle B (21–20) per month | Partial | 50% | Payroll generation exists but Cycle A/B separation based on employee salary_cycle field not confirmed as fully operational. | In PayrollService@generateRun($cycle): filter employees by employment_details.salary_cycle = $cycle. Create separate payroll_runs record per cycle. Validate date ranges: A=1st to last day, B=21st prior month to 20th current. | Critical | Finance / HR | Go-live blocker.
Compensation & Finance | Payslip Calculation Formula | Net = Gross (basic+HRA+special) + OT pay + Incentives + Reimbursements + Encashment − Deductions | Partial | 60% | Basic payslip structure exists. Incentives and reimbursements lack DB-backed flows. | Ensure PayrollService@calculateNet(): gross = basic+hra+special_allowance; ot = overtime_records sum for cycle; incentives = approved incentives for month; reimbursements = approved claims; encashment = approved encashment for payroll_run; net = gross+ot+incentives+reimbursements+encashment-deductions. All sourced from respective DB tables. | Critical | Finance | Go-live blocker if incentives/reimbursements missing.
Compensation & Finance | Incentives Module | Ad hoc incentive entries (type, amount, reason, month) by HR Admin/Director; requires Director approval; included in payslip | Missing | 0% | No dedicated incentives table/workflow. Only mentioned as TODO. | 1. Migration: incentives(id, employee_id, type ENUM, amount, reason, month, year, status, approved_by). 2. IncentiveController@store(): HR Admin or Director creates entry. Notify Director for approval. 3. On approval: status=approved. PayrollService picks up approved incentives for the payroll month. 4. UI: incentives list per employee on Finance dashboard. | Critical | Finance / HR | Go-live blocker. Payslip will be wrong without this.
Compensation & Finance | Reimbursements Module | Employee submits claim (category, amount, expense_date, receipt upload); manager approves; Finance includes in payslip | Missing | 0% | No dedicated reimbursements model or workflow. | 1. Migration: reimbursements(id, employee_id, category ENUM(travel/internet/meal/medical/other), amount, expense_date, receipt_path, month, year, status, approved_by, notes). 2. ReimbursementController@store(): employee submits with file upload. Validate MIME. Store outside webroot. Notify manager. 3. Manager approves → Finance includes in payslip run. 4. File download via signed URL. | Critical | Finance / HR | Go-live blocker.
Compensation & Finance | Payroll Approval Flow (Finance Sign-off) | HR Admin locks data → draft payslips generated → Finance reviews/adjusts → Finance approves → PDFs emailed | Partial | 50% | Lock and draft generation partially built. Finance sign-off and email delivery pending (depends on dompdf). | 1. Add payroll_runs.status transitions: draft→pending_approval→approved. 2. HR Admin: PayrollController@lock() sets locked_by + generates drafts. 3. Finance: PayrollController@approve() triggers PDF generation + email dispatch per employee. 4. Wire with dompdf (see PDF fix). | Critical | Finance | Go-live blocker.
Notifications | All 18 Notification Events | 18 distinct notification events per Section 3.6 — all roles covered | Partial | 60% | Core leave/OT/attendance notifications exist. Incentive approved, Reimbursement, Payroll ready, Probation due, 30-day new-hire, Review due notifications not confirmed. | Create missing Notification classes in app/Notifications/: IncentiveApprovedNotification, ReimbursementStatusNotification, PayrollReadyForApprovalNotification, ProbationDueNotification, NewHireCheckinDueNotification, ReviewReminderNotification. Each uses database channel only (no email). Dispatch from respective Service/Command. | High | HR / Operations
Notifications | Bell Icon Unread Count Badge | Real-time unread count via Livewire polling every 30 seconds | Completed | 100% | Confirmed. | No action required. | Low | UX
Notifications | Mark All Read Action | Mark all notifications as read for current user | Completed | 100% | Confirmed. | No action required. | Low | UX
Notifications | Prune Notifications >90 Days | Weekly Sunday cron to delete notifications older than 90 days | Missing | 0% | pulse:prune-notifications not implemented. | Create PruneNotifications command: DB::table('notifications')->where('created_at','<',now()->subDays(90))->delete(). Schedule: $schedule->command('pulse:prune-notifications')->weekly()->sundays()->at('02:00'). | Medium | Technical / Performance
Performance Management | Quarterly KPI Reviews | Q1 Jul–Sep, Q2 Oct–Dec, Q3 Jan–Mar, Q4 Apr–Jun; KPIs per department; self + manager review; final composite rating | Completed | 100% | Confirmed. | No action required. | Low | HR
Performance Management | Review Reminder Cron | Weekly Monday 09:00: notify employees + managers if QBR review due within 7 days | Missing | 0% | pulse:check-review-reminders not implemented. | Create CheckReviewReminders command: find performance_reviews where quarter end date within 7 days AND status != submitted. Dispatch ReviewReminderNotification to employee and reviewer. Schedule: $schedule->command('pulse:check-review-reminders')->weeklyOn(1,'09:00'). | Medium | HR / Operations
Performance Management | Promotion Flag | Manager can set promotion_flag on performance review | Completed | 100% | Confirmed. | No action required. | Low | HR
Onboarding / Offboarding | Onboarding Checklist (10 steps) | 10-step checklist per spec Section 3.8; equipment log; 30-day auto-notification to manager | Completed | 100% | Confirmed. | Verify 30-day check-in cron (pulse:check-newhire-checkin) is scheduled and wired to OnboardingNotification. | Low | HR
Onboarding / Offboarding | 30-Day New Hire Check-in Cron | Daily 08:00: notify manager when employee hits 30-day mark | Missing | 0% | pulse:check-newhire-checkin not implemented. | Create CheckNewHireCheckin command: query employees WHERE DATEDIFF(NOW(), employment_details.start_date) = 30. Dispatch NewHireCheckinDueNotification to manager. Schedule: $schedule->command('pulse:check-newhire-checkin')->dailyAt('08:00'). | Medium | HR / Operations
Onboarding / Offboarding | Probation Due Cron (10 days) | Daily 08:00: notify manager + HR Admin 10 days before probation_end_date | Missing | 0% | pulse:check-probation-due not implemented. | Create CheckProbationDue command: query employment_details WHERE probation_end_date = CURDATE() + INTERVAL 10 DAY. Dispatch ProbationDueNotification to manager + HR Admin. Schedule: $schedule->command('pulse:check-probation-due')->dailyAt('08:00'). | High | HR / Compliance
Onboarding / Offboarding | Offboarding Checklist + Final Settlement | 8-step offboarding; exit_records table; final settlement fed into Compensation module; experience letter | Completed | 100% | Confirmed. | No action required. | Low | HR / Finance
Document Management | Policy + Employee Doc Storage with Versioning | Company docs visible to all; employee docs scoped to individual + HR + Finance; version control | Completed | 100% | Confirmed. | No action required. | Low | HR
Document Management | Policy Acknowledgement | HR Admin flags doc as requiring confirmation; employee acknowledges; tracked in document_acknowledgements | Completed | 100% | Confirmed. | No action required. | Low | HR / Compliance
Document Management | Document Expiry Notification Cron | Daily 08:00: in-app notification to HR Admin for documents expiring in 30 days | Missing | 0% | pulse:check-document-expiry not implemented. | Create CheckDocumentExpiry command: query documents WHERE expiry_date = CURDATE() + INTERVAL 30 DAY AND expiry_date IS NOT NULL. Dispatch DocumentExpiryNotification to HR Admin. Schedule: $schedule->command('pulse:check-document-expiry')->dailyAt('08:00'). | Medium | HR / Compliance
Dashboard — Executive | Headcount Stats | Total active employees by department, shift, work mode | Missing | 0% | Executive dashboard not built. | Create ExecutiveDashboardComponent (Livewire). Query: Employee::where('status','active')->with('employmentDetail')->get(). Group by department_id, shift, work_mode. Render as stat cards. | High | HR / Operations
Dashboard — Executive | Today's Attendance Overview | % clocked in, WFH vs office, absences without approved leave | Missing | 0% | Not built. | In ExecutiveDashboardComponent: query attendance_logs for today. Calculate clocked_in_count/total_active*100. Cross-reference leave_requests for on-leave. Flag employees with no clock-in and no approved leave as absent. | High | Operations
Dashboard — Executive | Leave + Payroll + Performance Overview | Pending leave approvals company-wide; payroll cycle status; QBR completion %; alerts panel | Missing | 0% | Not built. | Add to ExecutiveDashboardComponent: leave_requests pending count; payroll_runs current status; performance_reviews completion rate; expiring docs + overdue onboarding tasks in alerts panel. | High | HR / Finance / Operations
Dashboard — Department Head | Team Attendance + Leave Calendar | Daily clock-in status per department; visual monthly team leave calendar; pending approvals with age indicator | Missing | 0% | Department dashboard not built. | Create DepartmentDashboardComponent scoped to auth()->user()->employee->employmentDetail->department_id. Team attendance widget + monthly leave calendar (FullCalendar.js or CSS grid). Pending approvals with created_at age badge. | High | Operations
Dashboard — Department Head | Team OT Summary | Team OT hours + amount for current month | Missing | 0% | Not built. | In DepartmentDashboardComponent: query overtime_records WHERE month+year=current AND employee in department. Sum ot_hours_worked and ot_amount. | Medium | Finance / Operations
Dashboard — Finance | Payroll Approval Queue (Cycle A + B) | Cycle A and B drafts ready for Finance review | Missing | 0% | Finance dashboard not built. | Create FinanceDashboardComponent. Query payroll_runs WHERE status='pending_approval'. Show both cycles side by side with total gross, OT, net. | Critical | Finance | Go-live blocker. Finance cannot do their job.
Dashboard — Finance | Monthly Payroll Summary by Department | Gross, OT, incentives, reimbursements, net by department + total | Missing | 0% | Not built. | In FinanceDashboardComponent: join payslips→payroll_runs→employees→employment_details. GROUP BY department_id. Sum all components. | High | Finance
Dashboard — Finance | Encashment + Incentives + Reimbursements Queue | Approved encashment requests, pending incentives, approved reimbursements for current cycle | Missing | 0% | Not built. Also depends on Incentives/Reimbursements modules being built first. | After building Incentives and Reimbursements modules, add widgets to FinanceDashboardComponent. | High | Finance | Depends on missing modules.
Dashboard — Employee | Attendance Widget + Leave Balances | Clock in/out button, work mode, break button, today's hours; CSL remaining, MDL days, Comp Off credits | Completed | 100% | Confirmed. | Verify Comp Off credits are shown once CO logic is built. | Low | HR / UX
Dashboard — Employee | Team Calendar (Colleagues on Leave) | Who is on leave this week — name + dates only | Completed | 100% | Confirmed. | No action required. | Low | UX
Scheduled Jobs | pulse:check-missing-checkouts — Daily 21:00 | Flag attendance_logs with no clock-out; send in-app notification to employee | Completed | 100% | Confirmed. | No action required. | Low | HR
Scheduled Jobs | pulse:check-leave-escalations — Hourly | Find leave requests pending > 24 hrs; notify HR Admin | Completed | 100% | Confirmed. | No action required. | Low | HR
Scheduled Jobs | pulse:check-late-arrivals — Daily 10:45 + 13:15 | Confirm late flags per shift; notify manager via in-app | Missing | 0% | Not implemented. | See shift_settings fix above. Schedule two runs: ->dailyAt('10:45') for IT shift and ->dailyAt('13:15') for UK shift. Pass shift parameter to command. | Critical | HR | Go-live blocker.
Scheduled Jobs | pulse:check-excess-breaks — Daily 20:00 | Sum break_logs per employee; flag + notify if > 60 mins | Missing | 0% | Not implemented. | Create command querying break_logs GROUP BY attendance_log_id HAVING SUM(duration_minutes)>60. Update attendance_logs.excess_break_flag. Dispatch notifications. Schedule: ->dailyAt('20:00'). | High | HR
Scheduled Jobs | pulse:check-ot-escalations — Hourly | OT requests pending > 24 hrs; notify HR Admin | Missing | 0% | Not implemented. | Mirror of leave escalations command for ot_requests table. Schedule: ->everyHour(). | High | HR
Scheduled Jobs | pulse:check-document-expiry — Daily 08:00 | In-app notification to HR Admin for docs expiring in 30 days | Missing | 0% | Not implemented. | See Document Management fix above. | Medium | HR / Compliance
Scheduled Jobs | pulse:check-probation-due — Daily 08:00 | Notify manager + HR Admin 10 days before probation end | Missing | 0% | Not implemented. | See Onboarding fix above. | High | HR / Compliance
Scheduled Jobs | pulse:check-newhire-checkin — Daily 08:00 | Notify manager when employee hits 30-day mark | Missing | 0% | Not implemented. | See Onboarding fix above. | Medium | HR
Scheduled Jobs | pulse:check-review-reminders — Weekly Monday 09:00 | Notify employees + managers if QBR review due within 7 days | Missing | 0% | Not implemented. | See Performance Management fix above. | Medium | HR
Scheduled Jobs | pulse:prune-notifications — Weekly Sunday | Delete notifications older than 90 days | Missing | 0% | Not implemented. | See Notifications fix above. | Medium | Technical
Scheduled Jobs | pulse:generate-attendance-summary — 1st of month 01:00 | Generate previous month attendance summary report per employee | Missing | 0% | Not implemented. | Create GenerateAttendanceSummary command: for each active employee, aggregate attendance_logs for previous month (total days, present, late, absent, OT hours, excess breaks). Store in attendance_summaries table or generate exportable report. Schedule: $schedule->command('pulse:generate-attendance-summary')->monthlyOn(1,'01:00'). | Medium | HR / Finance
Security & Audit | Audit Log Table (audit_logs) | Eloquent Observers log create/update/delete on employees, leave_requests, payslips, salary_structures, ot_requests. Columns: user_id, action, model_type, model_id, old_values JSON, new_values JSON, ip_address, created_at. Visible to Super Admin + HR Admin. Never pruned. | Missing | 0% | Not started. No observers implemented. | 1. Migration: create audit_logs with all columns per spec. 2. Create AuditObserver trait (or use spatie/laravel-activitylog). 3. Register observers in AppServiceProvider: Employee::observe(AuditObserver::class), LeaveRequest::observe(...), Payslip::observe(...), SalaryStructure::observe(...), OtRequest::observe(...). 4. In Observer methods: AuditLog::create(['user_id'=>auth()->id(), 'action'=>'updated', 'model_type'=>get_class($model), 'model_id'=>$model->id, 'old_values'=>json_encode($model->getOriginal()), 'new_values'=>json_encode($model->getDirty()), 'ip_address'=>request()->ip()]). 5. Route: Super Admin + HR Admin audit log viewer. | Critical | Compliance / Security | Go-live blocker. HR compliance requirement.
Security & Audit | HTTPS + CSRF + XSS Protection | TLS enforced; all forms @csrf; Blade escaping; file uploads MIME validated outside webroot | Completed | 100% | Standard Laravel protections in place. | No action required. | Low | Security
Security & Audit | Session Timeout + Password Policy | 8-hour inactivity timeout; bcrypt hashing; minimum 8 characters | Completed | 100% | Standard Laravel Auth. | No action required. | Low | Security

## Module Summary
PULSE v3.1 — MODULE-WISE COMPLETION SUMMARY
Module | Total Features | Completed | Partial | Missing | Deviated | Completion %
System Architecture | 8 | 3 | 2 | 1 | 2 | 50%
RBAC | 4 | 2 | 2 | 0 | 0 | 75%
Employee Management | 4 | 3 | 1 | 0 | 0 | 88%
Attendance | 7 | 3 | 3 | 0 | 1 | 64%
Leave Management | 5 | 1 | 3 | 2 | 0 | 50%
Overtime | 4 | 3 | 0 | 1 | 0 | 75%
Compensation & Finance | 5 | 0 | 2 | 3 | 0 | 20%
Notifications | 4 | 2 | 1 | 1 | 0 | 62%
Performance Management | 3 | 2 | 0 | 1 | 0 | 67%
Onboarding / Offboarding | 4 | 2 | 0 | 2 | 0 | 50%
Document Management | 3 | 2 | 0 | 1 | 0 | 67%
Dashboard — Executive | 3 | 0 | 0 | 3 | 0 | 0%
Dashboard — Dept Head | 2 | 0 | 0 | 2 | 0 | 0%
Dashboard — Finance | 3 | 0 | 0 | 3 | 0 | 0%
Dashboard — Employee | 2 | 2 | 0 | 0 | 0 | 100%
Scheduled Jobs | 11 | 2 | 0 | 9 | 0 | 18%
Security & Audit | 3 | 2 | 0 | 1 | 0 | 67%
TOTAL / OVERALL | 75 | 29 | 14 | 30 | 3 | 48%

## Go-Live Blockers
🚨 GO-LIVE BLOCKERS — MUST FIX BEFORE PRODUCTION
# | Module | Blocker Description | Risk if Ignored | Estimated Effort | Fix Reference
1 | System Architecture | Payslip PDF not generated via dompdf — cannot email payslips to employees | Employees never receive payslips. Finance process broken. | 2–3 days | Full Audit row: Payslip PDF
2 | System Architecture | SMTP email delivery for payslips not implemented | Legal obligation to deliver payslips unmet. | 1 day (after PDF fix) | Full Audit row: Email SMTP
3 | System Architecture | No DB backups (spatie/laravel-backup) | Total data loss on server failure with no recovery path. | 0.5 days | Full Audit row: DB Backups
4 | Employee Management | salary_cycle (A/B) not confirmed on employment_details | Cannot run separate Cycle A and Cycle B payroll. All payroll processing fails. | 0.5 days | Full Audit row: salary_cycle
5 | Leave Management | MDL blocking logic absent — december_mandatory_days not wired | Employees can apply leave on company shutdown days. Leave balance calculations incorrect. | 2 days | Full Audit row: MDL
6 | Leave Management | Leave Encashment not wired to Payroll run | Approved encashments never appear in employee payslips. Finance liability untracked. | 2 days | Full Audit row: Encashment
7 | Compensation & Finance | Incentives module does not exist (no DB model, no workflow) | Payslip net pay calculation is wrong — incentives missing. | 3–4 days | Full Audit row: Incentives
8 | Compensation & Finance | Reimbursements module does not exist | Expense claims never reach payslip. Employee complaints. Finance blind to liabilities. | 3–4 days | Full Audit row: Reimbursements
9 | Compensation & Finance | Cycle A/B payroll run separation not operational | All employees processed in one batch — incorrect pay dates and amounts. | 1–2 days | Full Audit row: Salary Cycle A/B
10 | Security & Audit | audit_logs table + Eloquent Observers not implemented | Zero HR compliance trail. Any payroll dispute or legal audit cannot be defended. | 2–3 days | Full Audit row: Audit Logs
11 | Scheduled Jobs | pulse:check-late-arrivals not running | No automated late flagging. Attendance discipline enforcement completely manual. | 1 day | Full Audit row: Late Arrivals Cron
12 | Dashboard — Finance | Finance Dashboard entirely missing | Finance (Emad) has no interface to review/approve payroll. Payroll process jammed. | 3–5 days | Full Audit row: Finance Dashboard

## Dev Roadmap
PULSE v3.1 — SUGGESTED DEVELOPMENT ROADMAP TO 100% COMPLIANCE
Sprint | Phase | Tasks | Est. Days | Priority | Outcome
Sprint 1 | 🔴 Blocker Fix — Finance Core | 1. Install dompdf + build PayslipPdf blade view 2. Wire SMTP email delivery for payslips 3. Build Incentives module (DB + workflow + Director approval) 4. Build Reimbursements module (DB + workflow + file upload) 5. Wire Encashment → Payroll net_pay calculation 6. Confirm salary_cycle A/B separation in PayrollService | 8–10 | Critical | Payroll can run end-to-end with correct net pay
Sprint 2 | 🔴 Blocker Fix — Compliance & Security | 1. Implement audit_logs migration + Eloquent Observers (5 models) 2. Implement spatie/laravel-backup with daily schedule 3. Build MDL (december_mandatory_days) blocking in LeaveService 4. Build Comp Off auto-credit logic 5. Seed public_holidays + wire into leave validation | 6–8 | Critical | HR compliance trail active; leave policy fully correct
Sprint 3 | 🟠 High Priority — Cron Jobs | 1. pulse:check-late-arrivals (with shift_settings integration) 2. pulse:check-excess-breaks 3. pulse:check-ot-escalations 4. pulse:check-document-expiry 5. pulse:check-probation-due 6. pulse:check-newhire-checkin 7. pulse:check-review-reminders 8. pulse:prune-notifications 9. pulse:generate-attendance-summary | 5–7 | High | All 11 cron jobs operational; automated HR management
Sprint 4 | 🟠 High Priority — Dashboards | 1. Executive Dashboard (Mazhar) — headcount, attendance, leave, payroll, performance, alerts 2. Finance Dashboard (Emad) — payroll queue, monthly summary, OT/incentives/reimbursements/encashment 3. Department Head Dashboard (Rustom/Nick/Nikita) — team attendance, leave calendar, OT summary | 7–10 | High | All 4 dashboards live; role-specific views complete
Sprint 5 | 🟡 Medium Priority — System Config & Security | 1. System Settings UI for Super Admin (shift config, MDL day setup, cycle assignment) 2. HR Admin partial access to system settings 3. Signed URL payslip download (5-min expiry) 4. OT and Incentive policies (OTPolicy, IncentivePolicy) 5. Missing notification classes (Incentive, Reimbursement, Probation, NewHire, ReviewReminder) | 4–5 | Medium | Security hardened; all RBAC policies complete
Sprint 6 | 🟢 Polish & QA | 1. Mobile responsiveness QA across all Livewire components 2. PDF/Excel reports export 3. Audit log viewer UI for Super Admin + HR Admin 4. End-to-end payroll flow test (Cycle A + B) 5. Full leave cycle test (CSL carry-forward, MDL block, Comp Off earn) 6. Security pen test checklist | 4–5 | Low | Production-ready; 100% spec compliance achieved

## Client Review Sheet
PULSE BY CONEXUS — CLIENT REVIEW SHEET ¦ Feature Verification & Sign-Off
Module | Feature | Status | Client Verification Required | Client Sign-Off (Date) | Remarks
System Architecture | Laravel 11 + MySQL 8 + Livewire 3 stack | Completed | No |  | Confirm server meets PHP 8.3 + MySQL 8 requirements.
System Architecture | Payslip PDF email delivery to employees | Missing | Yes |  | Critical. Confirm SMTP provider and email template approval.
System Architecture | Daily DB backups (30-day retention) | Missing | Yes |  | Confirm backup storage location (local vs S3).
RBAC | All 6 roles functional with correct access levels | Completed | Yes |  | Client to test each role login and verify access.
RBAC | System Settings — Super Admin full, HR Admin partial | Partial | Yes |  | Define which settings HR Admin Shivani should be able to change.
Employee Management | Employee profiles, CRUD, org chart | Completed | No |  | Demo walkthrough recommended.
Employee Management | salary_cycle (A/B) per employee | Partial | Yes |  | Client to confirm which employees are on which cycle.
Attendance | Clock in/out with IP logging + work mode | Completed | No
Attendance | Break logging — repeatable, informational only | Completed | No |  | Confirm breaks do NOT deduct from hours worked.
Attendance | Late flag per shift (IT 10:35 / UK 1:05) | Partial | Yes |  | Confirm grace period policy is still 5 minutes as per spec.
Attendance | Attendance Regularisation workflow | Completed | No |  | Demo approval flow to client.
Attendance | Shift settings configurable (shift_settings table) | Partial | Yes |  | Client to confirm shift hours and grace for both shifts.
Leave | CSL 12 days — no lapse, carry-forward | Completed | No |  | Confirm financial year July–June reset is not clearing balances.
Leave | MDL 6 days — December pre-blocked days | Partial | Yes |  | Client (Mazhar/Shivani) to provide exact December MDL dates per year.
Leave | Comp Off earning on MDL/public holiday work | Missing | Yes |  | Confirm Comp Off policy details and applicable holidays.
Leave | Public Holidays calendar | Missing | Yes |  | Client to provide list of applicable UK + India public holidays.
Leave | Leave Encashment → Payroll integration | Partial | Yes |  | Confirm encashment rate formula (daily rate = gross/working days?).
Overtime | Pre-approval OT workflow at ₹100/hr | Completed | No
Overtime | OT escalation after 24 hrs | Missing | Yes |  | Confirm escalation goes to HR Admin only or also Director.
Compensation | Incentives module (types + Director approval) | Missing | Yes |  | Client to confirm incentive types and approval chain.
Compensation | Reimbursements module (categories + receipts) | Missing | Yes |  | Client to confirm reimbursement categories and approval chain.
Compensation | Payslip PDF — earnings + deductions breakdown | Deviated | Yes |  | Client to approve payslip template design before development.
Compensation | Cycle A (1–31) and Cycle B (21–20) runs | Partial | Yes |  | Confirm which employees are on Cycle B currently.
Notifications | All 18 notification events active | Partial | Yes |  | Test notification delivery end-to-end in UAT.
Performance | Quarterly KPI reviews (Q1–Q4 July–June) | Completed | No |  | Client to define KPIs per department before go-live.
Onboarding | Onboarding 10-step checklist | Completed | No
Onboarding | Probation due alert — 10 days before | Missing | Yes |  | Confirm who receives notification: manager only or also HR Admin.
Documents | Policy acknowledgement tracking | Completed | No
Documents | Document expiry alert — 30 days before | Missing | Yes |  | Confirm document types that have expiry (contracts, visas, etc.).
Dashboard | Executive Dashboard (Mazhar) | Missing | Yes |  | Client (Mazhar) to review dashboard wireframe before build.
Dashboard | Finance Dashboard (Emad) | Missing | Yes |  | Client (Emad) to review dashboard wireframe before build.
Dashboard | Department Head Dashboard | Missing | Yes |  | Client department heads (Rustom/Nick/Nikita) to review wireframe.
Dashboard | Employee Self-Service Dashboard | Completed | No
Security | Audit log for payroll + leave changes | Missing | Yes |  | Critical compliance requirement. Confirm retention policy.
Security | Signed URLs for payslip downloads (5-min expiry) | Partial | Yes |  | Confirm if employees download via email link or in-app.

## Executive Summary
PULSE BY CONEXUS — EXECUTIVE AUDIT SUMMARY
OVERALL COMPLETION | 48%
Total Features Audited | 75
✅ Completed | 29
⚠️ Partial | 14
❌ Missing | 30
🔄 Deviated from Spec | 3
🚨 Go-Live Blockers | 12
🔴 Critical Priority Issues | 15
🟡 Medium Priority Issues | 12
Estimated Total Dev Days to 100% | 35–45 days